## Slide 1
IDAES PCM Benchmarking Plan (Mar 29 - Apr 23, 2026)
Goal: align GTEP-to-PCM conversion and quantify LMP deviation sources vs paper UC
By Mar 29 (Sun): Compare how GTEP expansion outputs convert to PCM-ready inputs; fact-check mapping logic.
Mar 30 - Apr 12 (2 weeks): Run PCM simulations for baseline and converted scenarios with clean manifests/log checks.
Apr 13 - Apr 19 (1 week): Compare results and analyze time-series aggregation error impacts on LMP trend/sign.
Apr 23 (Thu): Present conversion status, PCM benchmark results, and next-step recommendations at bi-weekly IDAES meeting.
Fact check: Mar 29, 2026 is Sunday; meeting target is Thursday, Apr 23, 2026.
Notes: Prepared as standalone planning slide for IDAES bi-weekly update. Timeline reflects requested 2-week PCM run and 1-week analysis window.